## Sheet1
project_id | sprint | task_id | task_name | owner | status | estimated_hours | actual_hours | start_date | end_date | dependencies
P1 | 1 | T101 | Build API Contract | Arun | Done | 8 | 7 | 2025-02-01 | 2025-02-02
P1 | 1 | T102 | Database Schema Finalization | Neha | In-Progress | 12 | 6 | 2025-02-01 | 2025-02-03 | T101
P1 | 1 | T103 | Backend Framework Setup | Raj | Delayed | 10 | 14 | 2025-02-01 | 2025-02-05
P1 | 1 | T104 | UI Wireframe Review | Kriti | Not-Started | 6 | 0 | 2025-02-02 | 2025-02-04
P1 | 2 | T201 | API Development Sprint 1 | Raj | In-Progress | 20 | 8 | 2025-02-05 | 2025-02-10 | T101
P1 | 2 | T202 | UI Components Setup | Kriti | Delayed | 18 | 20 | 2025-02-05 | 2025-02-10 | T104
P1 | 2 | T203 | Integration Prep | Arun | Not-Started | 8 | 0 | 2025-02-07 | 2025-02-10 | T102,T103